## Sheet1
Stream | Description | Feature ID | Design / document status | Defect ID | Delivery Status (Developed / NI / Under Development) | Action On | Delivery ETD | Test Status Pass / Failed | Input Data | Output Data | Remarks
WMS | Customer specific numbering for Complaints raised from Customer Portal | CS/F/H2/18/009 | Released |  | Developed | Shan Sir |  | Passed
WMS | Deriving Lat/Long in Ship Point Master | CS/F/H2/18/012 |  |  |  | Shan Sir
WMS | Ability to send email from Quotation & display total price | CS/F/H2/18/011 | Released |  | NI | Shan Sir
TMS | Provision to track a consignment based on customer serial number on closed customer portal | TMS/F/H2/18/053 | Released |  | NI | Reddy Sir | Need to plan for Dec and subsequent months
TMS | Create Booking Request Link in Maintain Account | CS/F/H2/18/01 | Released |  | NI | Reddy Sir | Need to plan for Dec and subsequent months
Both | Multiple customer access for a Single user | CS/F/H2/18/013 | Released |  | NI | Shan Sir / Reddy Sir | Need to plan for Dec and subsequent months
TMS | Vendor Portal | CS/F/H2/18/012 | Released |  | NI | Reddy Sir | Need to plan for Dec and subsequent months
TMS | Make Payment in Open Portal | CS/F/H2/18/004 | Released |  | NI | Reddy Sir | Need to plan for Dec and subsequent months
TMS | Rate calculator defect |  |  | EPE-9075 |  | Reddy Sir | 2018-09-28
TMS | Closed Portal - Booking Location |  |  | EPE-9074 |  | Reddy Sir | 2018-09-28
WMS | Manage Quotation - Print Error |  |  | EPE-9065 |  | Sridevi
WMS | RFQ Defects |  |  | EPE-9064 |  | Shan Sir
TMS | Contract Link in Customer Portal |  |  | EPE-9028 |  | Reddy Sir | 2018-09-28
TMS | Customer Portal View Payment Print |  |  | EPE-8997 |  | Reddy Sir | 2018-10-05
WMS | Stock report in Customer Portal |  |  | EPE-6304 |  | Shan Sir
TMS | Open Portal BR issues |  |  | EPE-8908 |  | Reddy Sir | Reddy:Cannot provide at this moment
TMS | Recent jobs section |  |  | EPE-8900 |  | Reddy Sir | 2018-10-05
TMS | Open Portal - Logistics Defects |  |  | EPE-8813 |  | Reddy Sir | Reddy:Cannot provide at this moment
TMS | Customer Portal - TMS Defects |  |  | EPE-8777 |  | Reddy Sir | 2018-10-05
WMS | Customer Portal - WMS Defects |  |  | EPE-8776 |  | Shan Sir
WMS | Doughnuts results rectification |  |  | EPE-9120 |  | Shan Sir
TMS | Booking Request to display all statustes in doughnut |  |  | EPE-9111 |  | Reddy Sir | 2018-10-05
TMS | Sequence of Statuses in Legends |  |  | EPE-9112 |  | Reddy Sir | 2018-10-05
TMS | Track and trace - (type of documents to be traced) |  |  | EPE-9113 |  | Reddy Sir | 2018-09-28
TMS | Recievers Name to be added in POD |  |  | EPE-9115 |  | Reddy Sir | New Requirement - could be taken in December month
TMS | Success / failure message & Instant Upload of documents uploaded through Bulk Upload |  |  | EPE-9150 |  | NA
TMS | Click & fetch results ability on Legends in Closed Portal. |  |  | EPE-9151 |  | Reddy Sir | New Requirement - could be taken in December month
TMS | Ability to hold of a Booking Request from Closed Portal. |  | Pending |  |  | Ramesh
TMS | Booking Request number & Status visibility in Track and Trace grid. Check box for Track Events CN selection. |  | Pending |  |  | Ramesh
TMS | Track & Trace –New tab to be added – Inputs a. BR- change delivery date. Prepone of delivery date - cannot exceed route master- transit time b. add notes - BR notes c. Put BR on hold |  | Pending |  |  | Ramesh
TMS | Default date range from Landing Screen across reports launched. Reports to be launched on Click of the link in the landing page with pre defined search criteria. | CS/F/H2/18/020 | Pending |  |  | Ramesh
TMS | Hover In Transit feature in Closed Portal. | CS/F/H2/18/021 | Pending |  |  | Ramesh
WMS | Order no, item wise & location wise search in inbound, outbound, ASN & Return order hubs of Customer Portal. |  |  | EPE-9152 |  | Shan Sir
TMS | Open Portal – Provision to request Warehouse Quotation. |  | Pending |  |  | Ramesh
TMS | Send email to "default sales person's" mail ID - Create New BR |  |  | EPE-9153 |  | Reddy Sir | New Requirement - could be taken in December month
TMS | Send email to "default sales person's" mail ID - Rate Calculator Compute |  |  | EPE-9154 |  | Reddy Sir | New Requirement - could be taken in Dec month
Customer Service | Customer Payment Status - Additional Information |  |  | EPE-9155 |  | Muthu Sir
TMS | Open Portal - Track BR/CN through Cust ref number. |  | Pending |  |  | Ramesh