## Sheet1
Sl No | Feature Reg ID | Activity | Change description | Change Type | Status | Sprint | Project | Release Date | Release Version
241 | TMS/F/H1/18/220 |  | Breaking a consignment into smaller consignments after few legs are executed | Feature | RVW in progress | Sep 17-28 | CKB
246 | TMS/F/H1/18/228 | Order Management | QBR- • Added Bill To Id edit field in header – Slide #20 - • Payment Type to load only Cash/Credit Regular BR- • Added Bill To Id edit field in Basic Info tab – Slide#12 - • • Payment Type to load only Cash/Credit - | Feature | ST Pending | Sep 03-14 | CKB | 2018-09-11 | 3.86
250 | TMS/F/H2/18/028 | Order Management | • Additional columns in Contract Details/Revenue Details popup – QBR- slide #27, regular BR - slide #43 o Weight, Weight UOM, Volume, Volume UOM, Chargeable Qty, Minimum Charge, Basic Charge | Feature | RVW Pending | Sep 17-28 | Searoad
#REF! | TMS_TAR197 | R&B | Vendor Rate per unit Volume_Trip Agent | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR196 | R&B | Vendor Rate per THU_Trip Agent | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR199 | R&B | Vendor Flat Rate per Trip | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR198 | R&B | Vendor Rate per Vehicle Type -Trip Level | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS/F/H1/18/096 | HHT-HUB | Hub Receipt - Label print (Consignment details with barcode) option should be available in HHT | Feature | Coding in progress | Sep 17-28 | Searoad
#REF! | TMS/F/H2/18/001 | Mobile | Inclusion of FC Execution number (Container ID) as an option to create Quick Trip in the Driver Trip log app | Feature | BP Released | Sep 17-28 | Searoad
#REF! | TMS/F/H2/18/002 | HHT-HUB | HHT:Add New BR to the Released trips by the HHT operator while loading | Feature | Project Review Pending | Sep 03-14 | Searoad | NA | NA
#REF! | TMS_TAR186 | R&B | Vendor Flat Rate Per Trip (Tendering) | Feature | Coding Pending | Sep 17-28 | Proconnect
#REF! | TMS/F/H2/18/046 | Order Management | BR Screens ---Enabling workflows | Feature | RVW Pending | Sep 17-28 | proconnect
#REF! | TMS/F/H2/18/103 | Planning & Execution | Trip Log Screens ---Enabling workflows | Feature | RVW Pending | Sep 17-28 | proconnect
#REF! | TMS_TAR209 | R&B | Fixed Consignee Charges - Group Contract | Feature | Coding Pending | Sep 17-28 | AAI
#REF! | TMS_TAR203 | R&B | Rate Per Trip Per Vehicle Type | Feature | Coding Pending | Sep 17-28 | Proconnect
#REF! | CS/F/H2/18/004 | Open Portal | Make Payment from Open Portal. | Feature | Coding Pending | Sep 17-28 | Product
#REF! | WMS_TAR168 | R&B | Monthly Pallet Rental | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | WMS_TAR167 | R&B | Handling In Out Charge -Volume | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR213 | R&B | Vendor Overnight Charge | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR214 | R&B | Vendor Pick up charge | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS/F/H2/18/041 | HHT-HUB | HT Freight Conversion, Sync option enhancements | Feature | ST Pending | Sep 03-14 | Searoad | 2018-09-14 | 3.88
#REF! | TMS_TAR232 | R&B | Vendor Rate per document | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR233 | R&B | Vendor Rate per Higher Volumetric Weight | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR184 | R&B | Rate Based on Trip CN count | Feature | Coding Pending | Sep 17-28 | Cameron
#REF! | TMS/F/H2/18/045 | Planning & Execution | Planning Changes - Tariff & rate related columns in Resource grids | Feature | RVW in progress | Sep 17-28 | Visy
#REF! | TMS_TAR234 | R&B | Customer VAS charge per Unit Volume | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR235 | R&B | Customer VAS charge per Unit Weight | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR236 | R&B | Customer VAS charge per BR | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS_TAR237 | R&B | Customer VAS charge per THU | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS/F/H2/18/053 -A | TMSSetup | Function Parameters- • Added function parameters – TMS/F/H2/18/053 – slide #2 o Basis for deriving BR Status – Booking Request THU & Qty/Actual Picked Up THU & Qty o Default value of Parameter “Delivery Complete for this Booking Request” in Trip Log – Checked/Unchecked | Feature | ST Pending | Sep 03-14 | Visy | 2018-09-11 | 3.86
#REF! | TMS/F/H2/18/053 -B | Execution | Trip Log- • Added “Delivery Complete for this Booking Request” check box in THU tab header – XXXX – slide #25 - TMS/F/H2/18/053 | Feature | ON HOLD Need discussion | Sep 17-28 | Visy
#REF! | TMS/F/H2/18/043 | HHT-HUB | HHT Freight Conversion, Sync option enhancements | Feature | ST Pending | Sep 03-14 | Searoad | 2018-09-14 | 3.88
#REF! | TMS/F/H2/18/042 - A | Execution | •Trip Log- Update Resources popup changes - o Converted Update Resources popup controls to grid - TMS/F/H2/18/042 – slide #12 o Added Vendor Reference no edit column, License Plate No to Update Resources popup | Feature | ST Pending | Sep 03-14 | Proconnect | 2018-09-12 | 3.87
#REF! | TMS_TAR217 | R&B | Dangerous Goods Surcharge | Feature | Project Review Pending | Sep 03-14 | CKB | 2018-09-19 | 3.91
#REF! | TMS/F/H2/18/058 -A | Planning | Old Planning UI- • Addition of View Resource Availability icon column in VERDHAS grids (applicable only for VEDH) – slide #38 - TMS/F/H2/18/058 • View Resource Availability popup to show availability of the selected resource on the plan date – slide #39 - TMS/F/H2/18/058 | Feature | ST in progress | Sep 03-14 | Visy | 2018-09-17 | 3.89
#REF! | TMS/F/H2/18/058 -B | Planning | New Planning UI – • View Resource Availability popup to show availability of the selected resource on the plan date (applicable only for VEDH) – Added in Create and Manage Trip Plan UIs (VEDH grids) – slide #8, 9 - TMS/F/H2/18/058 | Feature | Coding in progress | Sep 17-28 | Visy
#REF! | TMS/F/H2/18/054 | Product | ExtJS 6 migration for TMS | Feature | ST Pending | Sep 03-14 | Product | 2018-09-18 | 3.9
#REF! | TMS/F/H2/18/059 | Portal/Order Management | Addition of THU SERIAL NO as a document type in Closed Portal to enable track and trace for a serial number. Applicable for both grid view and map view. | Feature | ST Pending | Sep 03-14 | Visy | 2018-09-11 | 3.86
#REF! | CS/F/H2/18/010 | Portal/Order Management | Provision to track a consignment based on CUSTOMER SERIAL NUMBER on closed customer portal | Feature | ST Pending | Sep 03-14 | CKB | 2018-09-11 | 3.86
#REF! | RB/F/H1/18/033 | R&B | During BR revenue, BR revenue should be based on customer contract and if “Bill To” is defined on the BR, then pick “Bill To” as customer id, else pick the customer id available on the BR as it works currently. This need to be extended for other where contract and customer ids are derived – Revenue Protection. | Feature | Coding in progress | Sep 17-28 | CKB
#REF! | CAMPSS-1276 | OPen Portal | Here Map integration for multi trips | Feature | Completed | Sep 03-14 | Product | NA | NA
#REF! | TMS/F/H1/18/220 | Hub Management | • Addition of new FC Type – “Break Consignment” • THU Id and Serial no. columns in Output THU grid to be made editable + Help for this option • Hide Output THU Search criteria above the Output THU grid for this option • Hide Compute functionality below Input THU grid for this option | Feature | RVW Pending | Sep 17-28 | CKB
#REF! |  | Order Management | Customer Portal new UCD complainace | Feature | RVW Pending | Sep 17-28 | Product
#REF! | TMS_TAR052 | R&B | Fuel Surcharge | Feature | Project review Pending | Sep 03-14 | Visy | 2018-09-10 | 3.85
| TMS/F/H2/18/042 - B | Execution | Unified Resource Help in Update Resources popup of Trip Log. Continuation of TMS/F/H2/18/042 | Feature | Coding in progress | Sep 17-28 | Proconnect